The ACI Research Lab: A Blueprint

Shanghai University of Engineering Science  ·  Agentic Creative Intelligence  ·  toward 2030

1. Vision

The ACI Research Lab studies how creative capability survives, erodes, or grows as people work with agentic AI, and builds the AI that develops it. Its object is the hardest and least-measured part of the question about AI and work: not output, but the judgment, the material feel, and the sustained attention that creative disciplines are built on. Its method is to configure AI that withholds rather than completes, put it to work across design education and practice, and measure what it does to the people who use it.

2. The problem, and why now

Creative work is being rebuilt around agentic AI faster than anyone is studying what it does to the people who do it. In design, film, architecture, and music, systems that once suggested now decide, and the practitioner’s role slides from making to selecting. The question is not whether these systems raise output. It is what sustained use does to the capability the field depends on. Two outcomes are equally consistent with the present evidence. Delegation may erode that capability, as handing navigation, recall, and other skills to machines has eroded them. Or an agent built to develop rather than replace may deepen it. No one has shown which, because the field has no validated measure of creative capability, let alone a controlled account of how agents change it. That is a serious and specific gap, and it is the one this lab is built to close.

The problem is hard for reasons that outlast any one tool. Creative capability is largely tacit, so measuring it resists the usual instruments. Augmentation and atrophy occur together, so a gain in speed can hide a loss in judgment. And as several agents and models are coupled into one workflow, authorship, authority, and responsibility blur, so that even naming who made a decision becomes a research question.

The timing is not incidental. Agentic tools are entering studios and curricula now, and the habits students and professionals form over the next few years will harden into defaults. The infrastructure to study this on our own terms, self-hosted, China-native, inspectable down to the log, is available today. And the ideas the lab tests are already in public: the ACI monograph publishes in December 2026, and the lab is how its central claim gets tested rather than asserted. A lab that begins now can set the baseline. One that begins in three years will be measuring a settled world.

3. The dæmon: a SUES framing of the AI agent

Most agentic AI is built to complete. The assistant, the copilot, and the autonomous agent are each measured by the work they finish. The ACI Lab reframes the agent and defines ours by what it refuses to do. A dæmon withholds the finished artifact, requires the person to make and defend the governing decision, and leaves the resolution with the person. Where an assistant returns a result, a dæmon returns a harder question. This is the lab’s distinctive construct and its wager: that an agent built to develop a person can succeed where one built to serve them erodes their craft.

The four creative capabilities

Extended Engagement (Shape).  Sustained embodied immersion in a material or problem, held until form emerges.

Aesthetic Awareness (Style).  Trained discernment of what works and why.

Adaptive Coherence (Story).  Holding a work whole as its parts change.

Expressive Influence (Statement).  Making a work land on an audience.

When more than one is in play, the practitioner convenes them as a Creative Council, seated as Chairperson around one shared design object. The Council and the multi-model orchestration it stands against are research directions D3 and D4.

4. Position, benchmark, and 2030 objectives

The lab joins a field that now frames AI around augmenting rather than replacing human capability: Stanford HAI, the MIT Media Lab’s work on human-AI symbiosis, Carnegie Mellon’s Human-Computer Interaction Institute, and Georgia Tech’s Design and Intelligence Lab, alongside the design-cognition tradition at TU Delft and Tongji’s College of Design and Innovation. Its position is specific. It studies creative capability, not general productivity. Its instrument is the withholding dæmon, a construct those completion-oriented labs do not study. Its grounding is embodied practice and Chinese philosophy. Its infrastructure is China-native and self-hosted. And it works across four design populations rather than a single user study.

By 2030 the lab aims to hold five things. A validated, published instrument for the four capabilities, adopted beyond SUES. A configurable dæmon platform and a Creative Council method in open use. A sustained record in Design Studies, CHI, CSCW, and the design journals. A longitudinal dataset of human-agent creative work that no other group holds. And standing partnerships across Shanghai’s design and computing schools. The ambition is to become the reference point for the study of AI and creative capability, as a handful of labs became the reference for AI and language, and AI and vision.

5. Four populations

Design students.  Novices forming capability. The site for formation, transfer, and the design of the intervention.

Design faculty.  Expert educators whose own judgment and whose transmission of a craft are both at stake when students meet agents before mentors.

Design communities.  Collectives of practice, where the Council becomes a social form and shared purpose must hold across many practitioners and agents.

Design agencies.  Commercial studios under the pressure to ship, where a withholding intermediary meets its hardest test and orchestration runs at scale.

6. Research directions

D1. Capability formation (students)

The instrument.  Observable indicators of the four capabilities in studio work, derived from protocol and linkographic analysis and validated against blind expert assessment.

Mechanism.  Whether the dæmon develops capability beyond an unaided baseline, a completion tool, and a consent-only condition that pauses for approval without requiring articulation. The consent-only condition separates the effect from interruption and time. Prediction: articulation exceeds consent-only, which exceeds the completion tool, on a delayed post-test, with assignment by studio section to keep the arms clean. If articulation and consent-only converge, the account fails.

Fading and transfer.  The withdrawal schedule that yields autonomy rather than dependence, and near, far, and durable transfer against a completion-tool cohort.

D2. Expert practice and transmission (faculty)

Expert judgment.  Whether faculty who work through dæmons hold or lose their own judgment over sustained use.

Transmission.  What happens to the apprenticeship of design when students arrive with answers in hand, and which parts of a craft still require long formation.

D3. The Creative Council and collective creativity (communities)

The Council as social form.  Whether the practitioner-as-Chairperson arrangement extends from one person to a collective, and whether shared purpose holds across many practitioners and agents. Studied through participatory design and action research.

D4. Multi-model orchestration and authority (agencies)

Orchestration against the Council.  The manuscript sets the Council against the mechanical orchestrator that routes and aggregates agents through Mixture-of-Experts routing inside a model and the Model Context Protocol and Agent-to-Agent delegation between systems, letting coordinated action stand in for shared purpose. The question is whether an orchestration with a human at the head of the table preserves purpose where the mechanical one codifies it away.

WorkBuddy, challenge and opportunity.  WorkBuddy is mechanical orchestration shipping at scale: an Expert marketplace and Expert Teams that switch across Hunyuan, DeepSeek, GLM, Kimi, and MiniMax, built to complete. It is the strongest field case of orchestration codifying coordinated action, and the design challenge of reconfiguring a completion platform to seat the practitioner at the head.

7. Five design workflows to research

The lab studies the dæmon where design happens, across five workflows that span the four capabilities and the disciplines the studios and local industry work in. Each is an open-source pipeline with a decision the dæmon can hold, and each produces the logged record the methods read.

| Design domain | Open-source pipeline | Decision the dæmon holds | Capability |
| --- | --- | --- | --- |
| Environmental, architecture | Hunyuan image; Hunyuan3D via Modly | Site response, program, circulation, the parti | Extended Engagement, Adaptive Coherence |
| Automotive | Hunyuan image; Modly | Package hardpoints, proportion, stance, surface | Aesthetic Awareness |
| Graphic | Hunyuan image | Message, hierarchy, grid, type | Expressive Influence, Aesthetic Awareness |
| Motion, video | OpenMontage | Emotional arc and structure, at the proposal gate | Adaptive Coherence, Aesthetic Awareness |
| Product, 3D form | Modly (Hunyuan3D) | Form, silhouette, proportion, use | Aesthetic Awareness, Extended Engagement |

8. Methods

The lab studies its own instruments. Every dæmon session produces a dense record: the person’s prompts and decisions, the models’ responses, the tool and agent calls, the revisions and selections, and their timing. That record is primary data, read through three layers that triangulate.

Design-cognition analysis.  Protocol analysis of design moves in the Delft tradition (Cross, Christiaans and Dorst) and linkography (Goldschmidt), computed over the logged record rather than transcribed by hand.

Interaction and process mining.  Sequence and process models of the decision record (Markov-model process mining, with dialogue and engagement-profile clustering), holding in view that interaction volume is not learning, and that unproductive engagement must be told from productive struggle.

LLM-assisted qualitative analysis.  On-device open-source models assist open coding, keeping data in the lab, with human-AI hybrid codebooks, reported human-model agreement, and the researcher holding interpretive authority.

On this base sit the causal and field designs. A pre-registered controlled comparison with the consent-only condition and delayed post-tests. Longitudinal ethnography of agencies and faculty. Participatory and action research with communities. Computational reading of AI-generated records, triangulated with controlled study and situated fieldwork, is the standard the lab builds to. The interaction record is rich personal data, so the lab runs on informed consent and ethics approval, and the logs stay self-hosted and access-controlled.

9. Recommended stack: Tencent plus open-source

- Agent, tools, orchestration:  Tencent WorkBuddy on Hunyuan Hy3, sandboxed, with tool calling and MCP and model switching across Hunyuan, DeepSeek, GLM, Kimi, and MiniMax. Reusable dæmon behaviors package as WorkBuddy Skills. WorkBuddy is also the object of direction D4.

- Brain:  Hunyuan Hy3 by default, with any OpenAI-compatible endpoint, including local Ollama, for open weights.

- Creative generation:  Hunyuan3D, HunyuanVideo, and Hunyuan image.

- Speech in:  Whisper, or Tencent Cloud ASR.

- Voice out and clone:  CosyVoice or Chatterbox, or Tencent Cloud TTS.

- Face:  MuseTalk with LivePortrait, or Duix.Heygem for a fully local clone.

- Real-time interface:  OpenTalking or LiveTalking, for the WebRTC, interruptible pipeline.

- Memory:  a vector store over the ACI corpus and lab materials.

- Compute and hosting:  Tencent Cloud GPU or on-prem cards. WorkBuddy self-hosts via Lighthouse. Data stays in China.

- Instrumentation:  a session logger that captures every prompt, response, tool call, revision, and timing as the primary research record. This is the lab’s core research instrument.

10. Compute

Video and 3D generation are the heavy cost. Quantization with text-encoder offload to system RAM brings full-precision models onto one consumer GPU, so a prototype rig is inexpensive.

| Tier | GPU | System | Runs |
| --- | --- | --- | --- |
| 0 Prototype | 1x RTX 4090 24GB | 64GB RAM, 2TB NVMe | Dæmon LLM 7-14B quantized, image gen, Modly (Hunyuan3D Mini), short local video FP8, session logging |
| 1 Workstation | 1x 48GB (L40S) or 80GB (A100) | 128GB RAM, 4TB NVMe | WAN 14B or HunyuanVideo 720p FP8, Hunyuan3D full, larger dæmon LLM |
| 2 Cohort node | 2-4x 48-80GB, or Tencent Cloud GPU | 256GB+ RAM | Concurrent studio sessions plus overnight batch |

11. Target journals

| Focus | Primary | Secondary |
| --- | --- | --- |
| Students: capability formation | Design Studies; Journal of the Learning Sciences | Int. J. of Technology and Design Education; ACM Creativity and Cognition |
| Faculty: expert practice, transmission | Design Studies; Design Issues | She Ji; Int. J. of Technology and Design Education |
| Communities: the Creative Council | CoDesign; New Media and Society | ACM CSCW (PACMHCI); She Ji |
| Agencies: orchestration, authority | ACM CHI; Int. J. of Human-Computer Studies | Journal of Engineering Design; ACM TOCHI |

12. Shanghai partners

Confirm current principal investigators before approaching. Tongji and Donghua are the warm starts, through Yilin Wang and Joseph’s expert appointment.

| Institution | Group and strength | Fit | Entry |
| --- | --- | --- | --- |
| Tongji University, College of Design and Innovation | Design Engineering and Computing Research Lab (design cognition, affective computing); iDVx Lab (AI-supported design, HCI); publishes She Ji | Students, faculty, agencies | Yilin Wang; anchor |
| Shanghai Jiao Tong University, School of Design | Design with intelligent manufacturing and robotics; UX and HCI (Ting Han group) | Communities, agencies | Direct |
| Fudan University, School of Computer Science | Human-centered AGI and systems (Li Shang) | Agencies, orchestration | Direct |
| NYU Shanghai | Human-AI alignment and interaction (Hua Shen); CHI and CSCW | Agencies; co-authorship | Direct, English |
| East China Normal University, Psychology and Cognitive Science | Cognition, learning sciences, measurement | Students, faculty | Direct |
| Donghua University, School of Design | Design; Joseph’s foreign-expert host | Faculty, pilots | Warm |

13. People and resourcing

The lab is directed by Joseph Press, with Yilin Wang as co-lead and the anchor to Tongji. The near-term team is small and specific. A postdoctoral researcher or senior doctoral student leads the capability instrument and the controlled studies. A research engineer builds and maintains the dæmon platform and the logging pipeline. Two or three studio faculty serve as embedded collaborators who host the studies in their courses. An external advisory of design-cognition and human-AI researchers keeps the work honest against the field. Resourcing targets the National Natural Science Foundation of China and Shanghai municipal talent and innovation programs for the empirical work, and an industry partnership with Tencent for compute and platform access. None of this is yet secured, and the blueprint names the roles the program requires.

14. Risks and mitigations

- The instrument may not validate.  If the four capabilities resist a reliable measure, the causal program stalls. Treat instrument development as a result in its own right, and partner with a group that holds a validated design-cognition measure.

- The controlled study is hard to run cleanly.  A graded studio makes random assignment and a completion-tool arm fraught, and the arms can contaminate one another. Assign by studio section rather than within a class, counterbalance across the semester, and keep the completion-tool arm to non-graded exercises.

- Field access is slow.  Agencies and communities take time to recruit and to trust. Open those cases early and lead with the warm partners.

- WorkBuddy is a moving commercial target.  Its features and models will change under us. Treat it as one instance of orchestration rather than a dependency, and keep the open-source path, OpenMontage, Modly, and self-hosted models, as the stable base.

15. Plan to Chinese New Year 2027

The program runs from September 2026 to the Chinese New Year holiday on 6 February 2027. Establish the capability instrument with a first studio cohort while the prototype rig and session logger are stood up. Run the student mechanism study with the consent-only condition through the autumn. Open the WorkBuddy agency case and approach Tongji and NYU Shanghai in parallel, since field access takes time. The ACI book publishes on 22 December, with a campus launch event on 19 and 20 December. Close the period with first paper drafts and a phase review before the holiday. By the holiday the lab should hold three concrete results: a validated pilot of the capability instrument, one pre-registered study running in the field, and the first logged dataset. The weekly Gantt follows.

References. MIT Media Lab (skill erosion under AI assistance); Risko and Gilbert (cognitive offloading); Cross, Christiaans and Dorst (design protocols); Goldschmidt (linkography); Helske et al. (process mining for learning analytics); Buçinca et al. (cognitive forcing functions); Bjork (desirable difficulties); Barnett and Ceci (transfer); Bucciarelli, Schön (design ethnography, reflective practice); Frayling; Zimmerman, Forlizzi and Evenson (research through design); Press and Wang, Agentic Creative Intelligence (four capabilities, Creative Council, Chapter 5). Confirm editions before citing.

Plan (Gantt) to Chinese New Year 2027  ·  至 2027 春节的计划（甘特图）

| 2026 / 2027 | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Workstream / week | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 |
| Capability instrument 能力测量工具 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prototype rig + logger 原型机与日志 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics + pre-registration 伦理与预注册 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner engagement 合作方接洽 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student mechanism study 学生机制研究 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agency case (WorkBuddy) 机构案例 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Faculty + community 教师与社群 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data pipeline + analysis 数据管道与分析 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First paper drafts 首批论文初稿 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase review + next plan 阶段回顾与规划 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestones 里程碑 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ◆ | ◆ |  |  |  |  |  | ◆ |

Milestones 里程碑: campus launch 19-20 Dec  ·  ACI book publication 22 Dec  ·  Chinese New Year 6 Feb 2027 (plan horizon).   校内发布 12月19-20日  ·  ACI 书出版 12月22日  ·  春节 2027年2月6日（计划地平线）。

ACI 研究实验室：蓝图

上海工程技术大学  ·  智能体创作智能  ·  面向 2030

一、愿景

ACI 研究实验室研究：当人与智能体式 AI 协作时，创作能力如何存续、侵蚀或生长；并构建那种培养它的 AI。其对象是“AI 与工作”之问中最难、最少被测量的部分：不是产出，而是创作学科赖以立足的判断、材料手感与持久注意。其方法是：配置一种克制而非完成的 AI，让它在设计教育与实践中工作，并测量它对使用者的影响。

二、问题与“为何是现在”

创作工作正围绕智能体式 AI 重建，其速度快过任何人对“它对做事的人何为”的研究。在设计、电影、建筑与音乐中，曾只做建议的系统如今在做决定，从业者的角色由“制作”滑向“选择”。之问不在于这些系统是否提高产出，而在于持续使用对这个领域所依赖的能力做了什么。两种结果与现有证据同样相容：交托可能侵蚀能力，一如把导航、记忆及其他技能交给机器后所发生的；也可能一个为培养而非替代而造的智能体反而深化它。无人证明何者为真，因为这个领域连一套经验证的创作能力测量都没有，更不用说对智能体如何改变它的受控说明。这是一个严肃而具体的缺口，也正是本实验室要填补的。

这个问题之难，有超出任何单一工具的原因。创作能力大多是默会的，因而抵制常规仪器的测量。增强与退化同时发生，因而速度上的增益可能掩盖判断上的损失。而当多个智能体与模型被耦合进一个工作流，作者身份、权力与责任变得模糊，以至于“谁做了那个决定”本身也成了一个研究问题。

时机并非偶然。智能体工具正在进入工作室与课程，学生与从业者在未来几年形成的习惯，将硬化为默认。以我们自己的方式研究它的基础设施，自托管、国产、可检视至日志，今日即可得。而实验室所检验的思想已在公共之中：ACI 专著于 2026 年 12 月出版，而实验室正是其核心主张得以被检验、而非只被断言的途径。今日起步的实验室可以设定基线；三年后起步的，只能去测量一个已成定局的世界。

三、dæmon：SUES 对 AI 智能体的重新界定

大多数智能体式 AI 为完成而生。助手、副驾、自主代理，各以它们完成的活来衡量。ACI 实验室重新界定智能体，并以它拒绝去做什么来定义它。dæmon 克制交出成品，要求人亲自作出并为主导性决定辩护，把裁决留给人。助手送回一个结果，dæmon 则送回一个更难的问题。这是实验室的标志性构念，也是其赌注：一个为培养人而造的智能体，能在一个为服侍人而造、却侵蚀其手艺之处成功。

四项创作能力

持续投入（Extended Engagement，形）。  对材料或问题的持久具身沉浸，与之相守直到形态浮现。

审美感知（Aesthetic Awareness，格）。  对“什么行、为什么行”的受训判别。

适应性连贯（Adaptive Coherence，事）。  在各部分变化时守住整体。

表达影响力（Expressive Influence，意）。  让作品落到受众身上。

当不止一项在场时，从业者作为主席，围绕一个共享的设计对象，把它们召集为一个创作议会。议会与它所对立的多模型编排，是研究方向 D3 与 D4。

四、定位、对标与 2030 目标

实验室所入的领域，如今都把 AI 定位为“增强而非替代”人的能力：Stanford HAI、MIT Media Lab 的人–AI 共生研究、卡内基梅隆的人机交互研究所、以及佐治亚理工的设计与智能实验室，连同代尔夫特与同济设计创意学院的设计认知传统。其位置是具体的：研究创作能力而非一般生产力；其仪器是克制型的 dæmon，一个那些完成型实验室不研究的构念；其根基是具身实践与中国哲学；其基础设施国产且自托管；它跨四类设计人群展开，而非单一的用户研究。

到 2030：四项能力的经验证、已发表、并在 SUES 之外被采用的测量工具；一个可配置的 dæmon 平台与一套创作议会方法的公开应用；在 Design Studies、CHI、CSCW 及设计期刊的持续纯绩；一份无其他团队拥有的人–智能体创作纵向数据集；以及与上海设计与计算各学院的长期合作。野心是成为“AI 与创作能力”研究的参照点，就如少数几家实验室成为了“AI 与语言”、“AI 与视觉”的参照点。

五、四类人群

设计学生。  形成能力的新手。形成、迁移、以及干预本身之设计的现场。

设计教师。  资深教育者，当学生先遇答案、后遇导师时，他们自身的判断与一门手艺的传承皆悬于此。

设计社群。  实践的集体，议会在此成为一种社会形式，共享的目的须在众多从业者与智能体之间守住。

设计机构。  “必须交付”压力下的商业工作室，克制型中介在此遇最硬的考验，编排也在此规模化运转。

六、研究方向

D1. 能力形成（学生）

工具。  从工作室作业中经口语报告与连接图分析建立四项能力的可观测指标，并对照专家盲评验证。

机制。  dæmon 是否比无辅助基线、完成型工具、以及“只暂停求同意、不要求阐明”的同意条件更能培养能力？同意条件把效应与打断和耗时分离。预测：阐明优于同意，同意优于完成型工具（以延迟后测衡量），并按工作室分班以保持各组洁净。若阐明与同意趋同，此说即败。

撤除与迁移。  何种撤除节奏产出自主而非依赖；相对于用完成型工具的队列，增益是否呈现近迁移、远迁移与持久性。

D2. 专家实践与传承（教师）

专家判断。  经 dæmon 工作的教师，在持续使用下是守住还是失去自身判断。

传承。  当学生手握答案而来，设计的学徒之路将如何；一门手艺的哪些部分仍需长期养成。

D3. 创作议会与集体创作（社群）

作为社会形式的议会。  “从业者作主席”的安排能否由一人延展到集体，共享的目的能否在众多从业者与智能体之间守住。以参与式设计与行动研究来研究。

D4. 多模型编排与权力（机构）

编排对立议会。  手稿把议会与机械编排器相对立，后者通过混合专家（MoE）、模型上下文协议（MCP）与智能体间（A2A）委派来路由与汇聚，并让“协调一致的行动”顶替共享的目的。之问是：一种把一个人置于桌首的编排，是否在机械编排把目的编码掉之处守住了目的。

WorkBuddy：挑战与机会。  WorkBuddy 是规模化运转的机械编排：一个“专家”市场与“专家团队”，在 Hunyuan、DeepSeek、GLM、Kimi、MiniMax 间切换，为完成而生。它既是“编排把协调一致的行动编码化”的最强田野案例，也是“把一个完成平台重构为把从业者置于桌首”的设计挑战。

七、五个待研究的设计工作流

实验室在设计真正发生之处研究 dæmon，跨五个工作流，涵盖四项能力与工作室及本地产业所处的学科。每一个都是一条开源流水线，带一个 dæmon 可扣住的决定，且每一个都产出方法所阅读的日志记录。

| 设计领域 | 开源流水线 | dæmon 扣住的决定 | 培养的能力 |
| --- | --- | --- | --- |
| 环境、建筑 | Hunyuan 图像；经 Modly 的 Hunyuan3D | 场地回应、功能、流线、总体构思（parti） | 持续投入、适应性连贯 |
| 汽车 | Hunyuan 图像；Modly | 布置硬点、比例、姿态、曲面 | 审美感知 |
| 平面 | Hunyuan 图像 | 信息、层级、网格、字体 | 表达影响力、审美感知 |
| 动态、视频 | OpenMontage | 情感弧线与结构，在提案门 | 适应性连贯、审美感知 |
| 产品、3D 形态 | Modly（Hunyuan3D） | 形态、轮廓、比例、用途 | 审美感知、持续投入 |

八、方法

实验室研究自身的仪器。每一次 dæmon 会话都产生一份稠密的记录：人的提示与决定、模型的响应、工具与智能体的调用、修改与选择、以及它们的时序。这份记录即原始数据，经三层互相三角验证。

设计认知分析。  代尔夫特传统的设计动作口语报告分析（Cross、Christiaans 与 Dorst）与连接图（Goldschmidt），现在在日志记录上计算，而非手工转录。

交互与过程挖掘。  对决策记录的序列与过程建模（马尔可夫模型过程挖掘；对话与参与度画像聚类），并持告诫：交互量不等于学习，需将无效投入与有效的苦思区分开。

LLM 辅助的质性分析。  本地开源模型辅助开放编码，数据留在实验室，采用人–AI 混合编码手册、报告人–模型一致度，并由研究者掌握阐释权。

在此基础之上，是因果与田野设计：带同意条件的预注册受控比较与延迟后测；对机构与教师的纵向民族志；以及与社群的参与式与行动研究。对 AI 生成记录的计算式阅读，与受控研究及情境田野三角验证，是实验室对齐的标准。交互记录属敏感个人数据，故实验室以知情同意与伦理审批为前提，日志自托管并受访问控制。

九、推荐技术栈：腾讯加开源

- 智能体、工具、编排：  基于 Hunyuan Hy3 的腾讯 WorkBuddy，沙箱化，支持工具调用与 MCP，可在 Hunyuan、DeepSeek、GLM、Kimi、MiniMax 间切换。可复用的 dæmon 行为打包为 WorkBuddy Skills。WorkBuddy 也是方向 D4 的对象。

- 大脑：  默认 Hunyuan Hy3；任意 OpenAI 兼容端点（含本地 Ollama）覆盖开源权重。

- 创作生成：  Hunyuan3D、HunyuanVideo、Hunyuan 图像。

- 语音输入：  Whisper，或腾讯云 ASR。

- 语音输出与克隆：  CosyVoice 或 Chatterbox，或腾讯云 TTS。

- 面孔：  MuseTalk 配 LivePortrait，或 Duix.Heygem 做完全本地克隆。

- 实时界面：  OpenTalking 或 LiveTalking，提供 WebRTC、可打断的管线。

- 记忆：  在 ACI 语料与实验室材料上的向量库。

- 算力与托管：  腾讯云 GPU 或本地显卡；WorkBuddy 可经 Lighthouse 自托管；数据留在国内。

- 仪表化：  一个会话记录器，把每个提示、响应、工具调用、修改与时序捕获为主要研究记录。这是实验室的核心研究仪器。

十、算力

视频与 3D 生成是大头。配合量化并把文本编码器卸载到系统内存，可把全精度模型收进一张消费级 GPU，故原型机并不昂贵。

| 级别 | GPU | 系统 | 可运行 |
| --- | --- | --- | --- |
| 0 原型 | 1x RTX 4090 24GB | 64GB 内存，2TB NVMe | dæmon 大模型 7-14B 量化、图像生成、Modly（Hunyuan3D Mini）、短时本地视频 FP8、会话日志 |
| 1 工作站 | 1x 48GB（L40S）或 80GB（A100） | 128GB 内存，4TB NVMe | WAN 14B 或 HunyuanVideo 720p FP8、Hunyuan3D 完整版、较大 dæmon 大模型 |
| 2 团队节点 | 2-4x 48-80GB，或腾讯云 GPU | 256GB 以上内存 | 并发工作室会话，加夜间批量 |

十一、目标期刊

| 侧重 | 首选 | 次选 |
| --- | --- | --- |
| 学生：能力形成 | Design Studies；Journal of the Learning Sciences | Int. J. of Technology and Design Education；ACM Creativity and Cognition |
| 教师：专家实践、传承 | Design Studies；Design Issues | She Ji；Int. J. of Technology and Design Education |
| 社群：创作议会 | CoDesign；New Media and Society | ACM CSCW (PACMHCI)；She Ji |
| 机构：编排与权力 | ACM CHI；Int. J. of Human-Computer Studies | Journal of Engineering Design；ACM TOCHI |

十二、上海合作方

接洽前请核实现任负责人。同济与东华是可暖启的起点，经由 Yilin Wang 与 Joseph 的外专职任。

| 机构 | 团队与强项 | 契合 | 入口 |
| --- | --- | --- | --- |
| 同济大学设计创意学院 | 设计工程与计算研究室（设计认知、情感计算）；iDVx 实验室（AI 辅助设计、HCI）；主办 She Ji | 学生、教师、机构 | Yilin Wang；锚点 |
| 上海交通大学设计学院 | 设计结合智能制造与机器人；用户体验与 HCI（韩挺团队） | 社群、机构 | 直接 |
| 复旦大学计算机科学技术学院 | 以人为本的 AGI 与系统（Li Shang） | 机构、编排 | 直接 |
| 上海纽约大学 | 人–AI 对齐与交互（Hua Shen）；CHI 与 CSCW | 机构；合著 | 直接、英文 |
| 华东师范大学心理与认知科学学院 | 认知、学习科学、测量 | 学生、教师 | 直接 |
| 东华大学服装与艺术设计学院 | 设计；Joseph 的外专职任所在 | 教师、试点 | 可暖启 |

十三、团队与资源

实验室由 Joseph Press 主持，Yilin Wang 为共同负责人，亦是通往同济的锚点。近期团队精而小。一名博士后或高年级博士生主导能力测量工具与受控研究。一名研究工程师建设并维护 dæmon 平台与日志管线。两三名工作室教师作为嵌入式合作者，在课程中承接研究。一个由设计认知与人–AI 研究者组成的外部顾问组，使工作对齐于领域而不失严谨。资源上，经验研究面向国家自然科学基金与上海市人才及创新计划，算力与平台经由与腾讯的产业合作。以上均尚未落实，本蓝图列出的是计划所需的角色。

十四、风险与应对

- 工具或无法通过验证。  若四项能力抵制可靠测量，因果计划将停滞。把工具开发当作一项独立成果，并与已有经验证之设计认知测量的团队合作。

- 受控研究难以干净开展。  计入成绩的工作室使随机分配与完成型工具组在伦理与实践上都棘手，各组之间亦可能相互污染。按工作室分班而非班内分配、在整学期内平衡、并把完成型工具组限于不计分练习。

- 田野准入缓慢。  机构与社群需要时间招募与建立信任。尽早开启这些案例，并以可暖启的合作方为先。

- WorkBuddy 是移动的商业目标。  其功能与模型会在我们脚下变化。把它当作编排的一个实例而非依赖，并把开源路径（OpenMontage、Modly、自托管模型）作为稳定底座。

十五、至 2027 春节的计划

计划从 2026 年 9 月运行至 2027 年 2 月 6 日的春节假期。在搭起原型机与会话记录器的同时，以首个工作室队列建立能力测量工具。整个秋季开展带同意条件的学生机制研究。并行开启 WorkBuddy 机构案例，并接洽同济与上海纽约大学，因田野准入需时。ACI 书于 12 月 22 日出版，并于 12 月 19–20 日在校举行发布会。假期前以首批论文初稿与一次阶段回顾收尾。到假期，实验室应握有三项具体成果：能力测量工具的验证性试点、一项在田野中运行的预注册研究、以及首个日志数据集。周度甘特图如下。

参考文献。MIT Media Lab（AI 辅助下的技能侵蚀）；Risko 与 Gilbert（认知卸载）；Cross、Christiaans 与 Dorst（设计协议）；Goldschmidt（连接图）；Helske 等（学习分析的过程挖掘）；Buçinca 等（认知强制机制）；Bjork（合意难度）；Barnett 与 Ceci（迁移）；Bucciarelli、Schön（设计民族志、反思性实践）；Frayling；Zimmerman、Forlizzi 与 Evenson（研究通过设计）；Press 与 Wang，《智能体创作智能》。引用前请核对版本。

Plan (Gantt) to Chinese New Year 2027  ·  至 2027 春节的计划（甘特图）

| 2026 / 2027 | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Workstream / week | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 |
| Capability instrument 能力测量工具 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prototype rig + logger 原型机与日志 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethics + pre-registration 伦理与预注册 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner engagement 合作方接洽 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Student mechanism study 学生机制研究 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Agency case (WorkBuddy) 机构案例 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Faculty + community 教师与社群 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data pipeline + analysis 数据管道与分析 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First paper drafts 首批论文初稿 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase review + next plan 阶段回顾与规划 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Milestones 里程碑 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ◆ | ◆ |  |  |  |  |  | ◆ |

Milestones 里程碑: campus launch 19-20 Dec  ·  ACI book publication 22 Dec  ·  Chinese New Year 6 Feb 2027 (plan horizon).   校内发布 12月19-20日  ·  ACI 书出版 12月22日  ·  春节 2027年2月6日（计划地平线）。